|  |
| --- |
| Bakersfield College Timeline To Prepare ReportIn Response to ACCJC Recommendations |
| “The Report should demonstrate, and the visiting team will verify, that the institution has addressed the recommendations noted below, resolved the deficiencies, and now meets Eligibility Requirements and Accreditation Standards.” ACCJC letter, February 11, 2013 |
| Date | **Activity** |
| February 22 | Timeline and composition of Oversight Committee and Recommendation Teams presented to College Council. |
| February 27 | Timeline and composition of Oversight Committee and Recommendation Teams presented to Academic Senate. |
| March 1 | Research and Reporting Session with College Council, FCDC, ASC, Assessment, Curriculum, College Council, Staff Development, Budget, ISIT, PRC, and Admin Council |
| March 4 | Timeline and composition of Oversight Committee and Recommendation Teams presented to President’s Cabinet. |
| February 27-April 15 | Recommendation Teams (8 College recommendations & 4 District recommendations) begin meeting and preparing content.Oversight Committee provides ongoing support to Recommendation Teams and regular updates to Academic Senate, College Council and President’s Cabinet. |
| April 22 | Recommendation Teams (8 College recommendations & 4 District recommendations) submit all content to Oversight Committee. |
| April 22 – May 10 | Oversight Committee, working with Recommendation Team Leads, will review and finalize content. |
| May 15  | Academic Senate Meeting to review finalized content for the purpose of providing additional evidence.  |
| May 17 | College Council to review finalized content for the purpose of providing additional evidence. |
| May 20 | President’s Cabinet to review finalized content for the purpose of providing additional evidence.  |
| May 21 – July 25 | Editor will provide a single voice for the content provided, ensuring consistency of information, layout, and style. |
| July 18 | Oversight committee and Recommendation Teams review edited report. |
| July 25 | Submit final report to district office for August Board of Trustees Meeting. |
| August 8 | Report presented to Board of Trustees for first reading. |
| August 26 | College President shares the report with the college community.  |
| August 29 | Submit final report to district office for September Board of Trustees Meeting. |
| September 12 | Report presented to Board of Trustees for acceptance. |
| October 15 | Reported submitted to ACCJC. |