**2016-17 BC Pathways – The Renegade Roadmap**

***October 19,2016***

**Introduction:**

Over the last three years BC has been focusing on strengthening student success through Mentoring First Generation students, creating programs in Degree Works, instituting Multiple Measures, developing ADT’s, embedding matriculation in high schools, so what is next? Following the Strategic Directions model we would like to build an implementation team and plan for Bakersfield College’s unique flavor of guided pathways. This DRAFT is the beginning of a college-wide plan to focus and provide overarching guidance to BC’s Renegade Roadmap. It will be submitted to the Academic Senate, College Council, Educational Administrators, SALT and other campus committees for feedback. Please direct your input to jfulks@bakersfieldcollege.edu

**WHAT:**

In 2016 Bakersfield College was selected as one of 30 colleges nationally to participate in the AACC Pathways initiative, an institute-driven national program designed to help colleges as they create their own local college pathways with expert guidance and collaboration between colleges. The pathways application went through Academic Senate, College Council, and other presentations were made in September 2015. Submission for the program required a college-wide readiness survey be completed and turned in with the application (Sept 2015), used as part of the selection process, and showing that college-wide leadership were supportive. The college had a large number of focus group meetings discussing the book “Redesigning America’s Colleges” with documentation at <https://www.bakersfieldcollege.edu/employees/professional-development/book-discussion> followed by a statewide Pathways Institute at Bakersfield College with materials posted at <https://www.bakersfieldcollege.edu/conference/redesigning-community-colleges>

Additional materials available at <https://www.bakersfieldcollege.edu/president/aacc-guided-pathways>

**WHO: (this is a draft and these are suggestions please provide feedback on representatives and specific people)**

***Renegade Roadmap (Pathways) Core Team***

Lead: Janet Fulks, Institutional Effectiveness\*

Lesley Bonds, Pathways Team Lead

Grace Commiso, Student Affairs

Cindy Collier, Academic Affairs (& CTE)

Jennifer Johnson, Curriculum Committee

Kimberly Bligh, Student Support Services and Pre-collegiate pathway

Sarah Baron (part of Pathways Grant)

***Renegade Roadmap (Pathways) Implementation Task Force (includes Core Team)***

Executive Leadership: President or designee (Kate Pluta; Steve Waller)

4 Academic Senate Reps: (suggest) Matt Garrett, Talita Pruett, Josh Lewis ??? other volunteers

CSEA appointee:

CCA chair or designee

SGA President or designee and one student appointee:

Information Technology: Matt Jones

Professional Development: Reese Weltman,

Data Leads: Data Coach (Maria Wright), and Lisa Fitzgerald, District Research

Equity: Julian West ??Lisa King?

Rural Initiatives representative: Dual Enrollment Manger??

Web and Marketing: Shannon Musser, (Dylan)

Members at large: Nick Strobel, Jessica Wojtysiak

***Support Team*** – Shauna Turner (primary), ?? (secondary)

**HOW: Weekly meetings through the end of Fall 2016, Winter Institute and then evaluate meeting and training schedule**

|  |  |  |
| --- | --- | --- |
| **Timeline** | **Core Team Lays the Foundation** | **Leads** |
| October | Committee list and charge toGovernance committees for input and representatives.  Communications plan draft  Institute #4 Pre-conference work  Set up the Plan to  Work with Committee Structure  Develop Website**—**Shannon Musser | Janet and Lesley |
| **Timeline** | **Taskforce Build Web** | **Leads** |
| November  to  December | Focus group work – Co-coordinators  Draft Meta-majors definition and planning for Winter Institute & Survey development  Catalog Work  Renegade Roadmap (Pathways) Implementation Task Force  First meeting and planning  IEPI California Pathways meetings Dec | Maria Wright & Reese Weltman  Janet Fulks, Cindy Collier, Kimberly Bligh, Sarah Baron  Jennifer Johnson &??? |
| **January 2015** | **Strategic Directions Task Force Begins Work** | |
| January  Institute | ***Winter Institute to Design and review Meta-majors***  ***Catalog information***  ***Accreditation Bootcamp*** | |
| February 2-4 | **Pathways Institute #2** | |
| January  February and  March | **Pathway Work Groups:**  College Committees  Academic Senate ISIT College Council  Curriculum Facilities Administrative Council (January)  Assessment FCDC Professional Development  Program Review AIQ Budget   * General:   + 1-3 at Panorama Campus   + 1 at Delano | |
| March | **Task Force Retreat:** What are the strategic directions? | |
| March  and  early April | **Writing** | |
| April | **Presentations to College Community** | |
| May | **College Council and Academic Senate vote** | |

**DELIVERABLES:**

* Website that includes the primary document as well as all the supporting materials.
* Criteria for areas of study or meta majors
* Survey for Meta-majors feedback
* Draft list of meta-majors
* Program pathway maps – completed by program faculty but organized by this taskforce
* Worksheets to enable pathways to complete above maps
* Agenda for winter institute
* Coordination with catalog rewrite including formatting from paper to web

**Taskforce Charge**: The focus of this taskforce is to implement the BC version of Pathways. This taskforce will be the central communication hub for pathways with required reporting to groups they represent. The taskforce will work with assigned areas to discuss meta-majors/areas of study and help coordinate information needed and documentation of pathways detail. The committee will suggest, plan and deliver professional development at the winter and summer institutes and other meetings as determined by the taskforce. The taskforce will lead the ground work on the implementation plans pre and post AACC institutes.

The taskforce will help create the website for the Pathways webpage and any written materials for communication. It is likely that these members will play a role in writing key documents for accreditation related to pathways.

Immediate work products this committee will land before Spring 2017 semester are:

* Criteria for areas of study or meta majors
* Draft list of meta-majors
* Program pathway maps – completed by program faculty but organized by this taskforce
* Worksheets to enable pathways to complete above maps
* Agenda for winter institute
* Coordination with catalog rewrite including formatting from paper to web
* Pathways web-update